## DevChecklist
Phase | Task | Priority | Owner Tool | Due | Status | Progress | Acceptance / Evidence | Notes
P0 Scope / Competition | Review Scope Baseline D01–D10 | P0 | Human | 2026-08-20 | Done | 100% | Human approval + decision log | D01–D10 confirmed; Development Baseline v1.0 generated
P0 Scope / Competition | Review PRD v0.1 | P0 | Human | 2026-08-21 | Review | 90% | PRD comments resolved | PRD promoted to v1.0 baseline; human document review still recommended
P0 Scope / Competition | Review SA/SD Development Baseline v1.0 | P0 | Codex | 2026-08-22 | Review | 90% | Architecture review; no blocker | SA/SD promoted to v1.0 after ADR-001–010 confirmation
P0 Scope / Competition | Freeze ADR-001–010 / stack decisions | P0 | Codex | 2026-08-24 | Done | 100% | ADR-001–006 approved | ADR-001–010 frozen in docs/18_ARCHITECTURE_DECISIONS.md
P0 Scope / Competition | Competition proposal v1 | P0 | Human | 2026-08-25 | In Progress | 50% | Internal review ready
P0 Scope / Competition | AI Use Case deck content v1 | P0 | Human | 2026-08-25 | In Progress | 50% | 20 slides max; scoring mapping
P0 Scope / Competition | Verify official upload form fields / demo requirement | P0 | Human | 2026-09-01 | Not Started | 0% | Capture exact required fields
P0 Scope / Competition | Final proposal + deck QA | P0 | Shared | 2026-09-05 | Not Started | 0% | Page count, naming, no customer data
P0 Scope / Competition | Upload rehearsal | P0 | Human | 2026-09-06 | Not Started | 0% | Files accepted by form
P0 Scope / Competition | Submit initial-review files | P0 | Human | 2026-09-07 | Not Started | 0% | Submission confirmation
P1 First Vertical Slice | Git repo bootstrap + initial checkpoint | P0 | Human | 2026-08-26 | Review | 90% | Generated repo/bundle exists; target Windows git status + preflight must pass | Generated Git-ready repo + bundle; target Windows clone/bootstrap still to verify
P1 First Vertical Slice | Shared skills/rules discovery check in 3 tools | P0 | Shared | 2026-08-27 | Not Started | 0% | All three tools see repo skills
P1 First Vertical Slice | Domain entities + repository interfaces | P0 | Codex | 2026-08-30 | Not Started | 0% | Unit tests + architecture review
P1 First Vertical Slice | SQLite metadata + migration skeleton | P0 | OpenCode | 2026-09-01 | Not Started | 0% | Migration smoke test
P1 First Vertical Slice | Event ledger + run states | P0 | Codex | 2026-09-02 | Not Started | 0% | State transition tests
P1 First Vertical Slice | Artifact/context/evidence baseline | P0 | Codex | 2026-09-03 | Not Started | 0% | Round-trip persistence tests
P1 First Vertical Slice | Extension registry + manifest skeleton | P1 | OpenCode | 2026-09-04 | Not Started | 0% | Registry tests
P1 First Vertical Slice | Minimal workflow runner | P0 | Codex | 2026-09-05 | Not Started | 0% | Workflow unit/integration tests
P1 First Vertical Slice | One runtime adapter vertical slice | P0 | OpenCode | 2026-09-06 | Not Started | 0% | Project→Review→Evidence E2E
P2 Core Product | Discuss workflow | P0 | OpenCode | 2026-09-10 | Not Started | 0% | Golden Discuss tests
P2 Core Product | Review workflow + findings/severity | P0 | OpenCode | 2026-09-11 | Not Started | 0% | Artifact review integration
P2 Core Product | Validate workflow + hard gates | P0 | Codex | 2026-09-12 | Not Started | 0% | Tool FAIL blocks Verified PASS
P2 Core Product | Council parallel analysis + cross review | P0 | Codex | 2026-09-14 | Not Started | 0% | Partial failure tests
P2 Core Product | Codex deep runtime adapter | P0 | Codex | 2026-09-16 | Not Started | 0% | Run/status/cancel/evidence/cleanup conformance
P2 Core Product | OpenCode deep runtime adapter | P0 | OpenCode | 2026-09-17 | Not Started | 0% | Run/status/cancel/evidence/cleanup conformance
P2 Core Product | Doctor + compatibility matrix | P0 | OpenCode | 2026-09-18 | Not Started | 0% | Version/maturity display
P2 Core Product | Core product milestone acceptance | P0 | Antigravity | 2026-09-20 | Not Started | 0% | Independent E2E + actual evidence
P3 Web / Local / Policy | LocalModelEndpoint contract | P0 | Codex | 2026-09-22 | Not Started | 0% | Contract review/tests
P3 Web / Local / Policy | LM Studio / Generic OpenAI-compatible profile | P0 | OpenCode | 2026-09-24 | Not Started | 0% | Discovery/stream/result
P3 Web / Local / Policy | Ollama profile | P1 | OpenCode | 2026-09-25 | Not Started | 0% | Discovery/stream/result
P3 Web / Local / Policy | WebSurface contract + companion boundary | P0 | Codex | 2026-09-25 | Not Started | 0% | No vendor DOM in core
P3 Web / Local / Policy | ChatGPT Web Level 3A | P0 | OpenCode | 2026-09-28 | Not Started | 0% | Launch/fill/capture/fallback
P3 Web / Local / Policy | Claude Web Level 3A | P1 | OpenCode | 2026-09-30 | Not Started | 0% | Launch/fill/capture/fallback
P3 Web / Local / Policy | Gemini Web Level 3A | P1 | OpenCode | 2026-10-02 | Not Started | 0% | Launch/fill/capture/fallback
P3 Web / Local / Policy | Browser E2E / fallback milestone | P0 | Antigravity | 2026-10-03 | Not Started | 0% | Driver failure does not break core
P3 Web / Local / Policy | Data classification + routing + Local-only | P0 | Codex | 2026-10-04 | Not Started | 0% | No silent sensitive cloud fallback
P4 Product Completion | 9 built-in workflow templates complete | P1 | OpenCode | 2026-10-09 | Not Started | 0% | Template validation + smoke runs
P4 Product Completion | Backup / restore | P0 | OpenCode | 2026-10-10 | Not Started | 0% | Restore from fresh workspace
P4 Product Completion | Schema migration acceptance | P0 | Codex | 2026-10-11 | Not Started | 0% | Old data migration + backup gate
P4 Product Completion | Budget / timeout / concurrency guard | P1 | OpenCode | 2026-10-12 | Not Started | 0% | Limits tested
P4 Product Completion | Usage / quality metrics baseline | P1 | OpenCode | 2026-10-13 | Not Started | 0% | Finding/fallback metrics
P4 Product Completion | UX progressive disclosure pass | P0 | Antigravity | 2026-10-14 | Not Started | 0% | User journey / dead-end report
P4 Product Completion | Four golden workflow deep regression | P0 | Shared | 2026-10-16 | Not Started | 0% | Current evidence bundle
P4 Product Completion | Feature freeze readiness review | P0 | Codex | 2026-10-18 | Not Started | 0% | No blocker / scope frozen
P5 Hardening / Acceptance | Full regression + failure injection | P0 | OpenCode | 2026-10-22 | Not Started | 0% | Actual test report
P5 Hardening / Acceptance | Cancel / timeout / child cleanup verification | P0 | Antigravity | 2026-10-24 | Not Started | 0% | Process evidence
P5 Hardening / Acceptance | Security / secret / egress review | P0 | Codex | 2026-10-25 | Not Started | 0% | No critical finding
P5 Hardening / Acceptance | Backup / restore / migration final test | P0 | OpenCode | 2026-10-26 | Not Started | 0% | Fresh restore evidence
P5 Hardening / Acceptance | Packaging / clean install test | P0 | Antigravity | 2026-10-28 | Not Started | 0% | Clean install walkthrough
P5 Hardening / Acceptance | Final compatibility matrix + known limitations | P1 | OpenCode | 2026-10-29 | Not Started | 0% | Published docs
P5 Hardening / Acceptance | V1 RC final acceptance | P0 | Shared | 2026-10-31 | Not Started | 0% | PASS/FAIL/NEED ACTION with evidence

## Dashboard
PolyNexus V1 Project Dashboard
KPI | Value | Phase Progress
Tracker Baseline Date | 2026-08-17 | Phase | Progress
Initial Review Deadline | 2026-09-07 | P0 Scope / Competition | 48%
Feature Freeze | 2026-10-18 | P1 First Vertical Slice | 10%
V1 Acceptance Complete | 2026-10-31 | P2 Core Product | 0%
Overall Task Progress | 11.18% | P3 Web / Local / Policy | 0%
Open Blockers | 0 | P4 Product Completion | 0%
|  | P5 Hardening / Acceptance | 0%
Hard Gate | Rule | Key Dates / Gates
Single Active Writer | Only one AI tool writes to the active branch at a time | 2026-08-25 | Competition content v1
Deterministic PASS | Real command/tool evidence and exit codes decide PASS | 2026-09-07 | Initial review submission
Scope Control | New feature must replace planned work or move to Future | 2026-09-20 | Core product gate
Token Control | Delta handoff; no repeated full-repo reading | 2026-10-18 | Feature freeze
Feature Freeze | No new features after 2026-10-18 | 2026-10-31 | V1 acceptance complete

## Milestones
Milestone | Target Date | Exit Criteria | Status | Owner | Evidence / Link | Notes
Scope Baseline Freeze | 2026-08-20 | D01-D10 + PRD/SA/SD logical baseline reviewed | Review | Human | docs/18_ARCHITECTURE_DECISIONS.md + docs/22_BASELINE_VALIDATION_REPORT.md | Architecture frozen; local target verification pending
Competition Content v1 | 2026-08-25 | Proposal + 20-slide outline 80–90% ready | In Progress | Human
First Vertical Slice | 2026-09-06 | Project→Review→Runtime→Evidence→Result works | Not Started | Shared
Initial Review Submission | 2026-09-07 | Required files uploaded; upload form checked | Not Started | Human
Core Product Gate | 2026-09-20 | Discuss/Review/Validate + Council + Codex/OpenCode core path | Not Started | Shared
Integration Gate | 2026-10-04 | Web AI + Local AI + Policy baseline usable | Not Started | Shared
Feature Freeze | 2026-10-18 | No new features; only fixes/tests/docs | Not Started | Human
V1 Acceptance Complete | 2026-10-31 | Golden workflows, migration, backup, conformance accepted | Not Started | Shared

## Competition
Item | Source / Rule | Internal Due | Status | Evidence / File | Notes
Proposal plan ≤20 pages | Original competition brief attachment 2 | 2026-09-05 | In Progress | PolyNexus_Cyber4_Initial_Proposal_Draft_v0.1.docx | A4 portrait; final font/page rules recheck
AI Use Case deck ≤20 pages | Original brief + current event site | 2026-09-05 | In Progress | docs/14_COMPETITION_SLIDE_OUTLINE.md | PPTX/PDF after content freeze
Verify actual upload form fields | Latest event site Microsoft Forms | 2026-09-01 | Not Started |  | Critical: old brief/current site differ on Demo wording
Demo / image requirement | Verify latest form/notice | 2026-09-02 | Not Started |  | Do not assume old 3-min or current 5–10-min text
Benefit explanation / effectiveness sheet | Current event site lists benefit explanation | 2026-09-03 | Not Started |  | Confirm whether separate attachment
No customer data/project content | Competition rules | 2026-09-05 | Not Started |  | Use synthetic/public project only
Scoring mapping 50/30/20 | Enterprise Value / Maturity / Innovation | 2026-08-30 | Not Started |  | Each major section supports a score dimension
File naming / size / format | Actual upload form | 2026-09-04 | Not Started
Upload rehearsal | Internal gate | 2026-09-06 | Not Started
Final submission | Latest notice | 2026-09-07 | Not Started |  | Capture confirmation

## Risks
ID | Risk | Severity | Owner | Mitigation | Status | Trigger / Review Date
R01 | Runtime/version integration matrix explosion | High | Codex | Certified matrix + Doctor + Conformance | Open | 2026-09-20
R02 | Web AI UI/login changes | High | Antigravity | Thin drivers + mandatory fallback + failure isolation | Open | 2026-10-03
R03 | UX becomes technical control panel | High | Human | Progressive disclosure; three primary entrances | Open | 2026-10-14
R04 | Scope exceeds Oct deadline | High | Human | CORE/BASELINE/COMPATIBILITY/FUTURE + feature freeze | Open | 2026-09-20
R05 | Three AI tools overwrite each other | High | Human | Single Active Writer + Git + handoff | Open | 2026-08-27
R06 | Token/quota waste from repeated context | High | Shared | Memory pyramid + diff review + routing | Open | 2026-09-06
R07 | AI consensus mistaken for evidence | High | Codex | Evidence types + hard gates | Open | 2026-09-12
R08 | Local route leaks via external tools | High | Codex | Route-level policy / Local-only | Open | 2026-10-04
R09 | Schema evolution breaks old workspaces | High | Codex | Versioned schema + migration + backup | Open | 2026-10-11
R10 | Competition submission requirement changes | High | Human | Verify actual form/latest notice | Open | 2026-09-01

## ToolAllocation
Tool | Target Task Share | Primary Role | Use For | Avoid | Quota Strategy
Codex | 35% | Architecture / Core | Contracts, domain, hard bugs, critical review | Routine templates/tests | Reserve high reasoning for high-coupling decisions
OpenCode | 55% | Implementation / Tests | Features, fixtures, conformance, templates, routine refactor | Changing confirmed architecture on its own | Primary workhorse; narrow context
Antigravity | 10% | Browser / E2E / Red Team | Web companion, user journey, milestone verification | Every-commit third review | Reserve quota for browser-heavy tasks
Human | 0% | Scope / Final Decision | Scope, competition narrative, approval, prioritization | Delegating final governance to AI | Manual checkpoints
Shared Rule | 100% | Single Active Writer | One writer + necessary reviewer; 3 tools only at milestone/RC |  | Delta handoff

## Sources
Source | Purpose | URL / Note
Cyber4.0 event site | Current event description / scoring / upload link | https://ai-challenge-2026.cybersoft.tw/
Competition brief | Original proposal format, page limits, categories | Cyber4_2026_AI競賽活動簡章.docx (user library)
Codex Skills docs | Repo skills path / progressive disclosure | https://developers.openai.com/codex/build-skills
OpenCode Skills/Rules docs | AGENTS.md + .agents/skills compatibility | https://opencode.ai/docs/skills/ ; https://opencode.ai/docs/rules/
Antigravity Skills/Rules docs | .agents/skills + .agents/rules workspace convention | https://antigravity.google/docs/skills ; https://antigravity.google/docs/rules-workflows